## Slide 1: HUM 4103 Project Planning and Management
Prepared By-
Md. Rejoan Chowdhury
Lecturer
Dept. of Civil Engineering
University of Global Village (UGV), Barishal

## Slide 2
Course Learning Outcomes (CLOs): After completing this course, students will be able to-
CLO 01 Understand the concepts of project planning and management.
CLO 02 Distinguish PERT and CPM.
CLO 03 Create bar chart and project status report.
CLO 04 Apply PDCA for continuously developed projects.
CLO 05 Determine time estimates, critical path, internal rate of return, payback
period, net present value, schedule and cost status.
CLO 06 Evaluate status of a project.
Project Planning and Management
COURSE CODE: HUM 4103 CREDIT: 04
MID EXAMINATION: 2 HOURS CIE MARKS: 120
SEMESTER END EXAMINATION: 3 HOURS SEE MARKS: 80

## Slide 3
Sl. | Course Contents | Hours | CLOs
1 | Project, elements and characteristics of project, project planning, project management, achievement of project management, role of project manager, characteristics of an effective project manager. | 6 | CLO 1
2 | Activity, schedule, bar chart and its development. | 2 | CLO 3
3 | Phases of project management, CPM, PERT, objective of PERT and CPM, critical path, critical path evaluation, expected time, comparison of PERT and CPM. | 4 | CLO 2
4 | Optimistic, pessimistic and most likely time estimate, expected time and standard deviation, critical path determination, benefits and limitations of PERT. | 6 | CLO 5
5 | Internal rate of return, payback period, suitability and benefits of payback period, determination of internal rate of return, payback period and net present value. | 4 | CLO 5
6 | Introduction to PDCA, use of PDCA, four steps, practical example, benefits. | 2 | CLO 4

## Slide 4
Sl. | Course Contents | Hours | CLOs
7 | Project monitoring, objectives, questions to be answered, earned value analysis, benefits, calculation, gathering work performance information, determination of schedule status and cost status. | 4 | CLO 5
8 | Project review, objectives, benefits, three tiers of players, steps to conduct a review, categories of project review, project status reports and purposes, structure of a project status report. | 4 | CLO 6

## Slide 5
Week | Topic | Teaching Learning Strategy | Assessment Strategy | CLOs | Page No.
1 | Concepts of project and Program | Lecture, Discussion | Mid, Final | CLO 1 | 8-17
2-3 | Concepts of project planning and management | Lecture, Discussion | Mid, Final | CLO 1 | 18-32
4 | Project scheduling (bar chart) | Lecture, Discussion | Assignment, Mid, Final | CLO 3 | 33-42
5-6 | PERT and CPM | Lecture, Discussion | Assignment, Mid, Final | CLO 2 | 43-64
7-9 | PERT: Time estimates | Lecture, Discussion | Assignment, Class Test, Mid, Final | CLO 5 | 65-79
10-11 | Cashflow analysis | Lecture, Discussion | Problem solving, Class Test, Final | CLO 5 | 80-84
12 | PDCA | Lecture, Discussion | Mid, Final | CLO 4 | 85-95

## Slide 6
Week | Topic | Teaching Learning Strategy | Assessment Strategy | CLOs | Page No.
13-14 | Project monitoring and earned value management | Lecture, Discussion | Case study, Final | CLO 5 | 96-112
15-16 | Project review | Lecture, Discussion | Final | CLO 6 | 113-129
References
1. Project Planning & Control With PERT & CPM - Dr. B.C. Punmia & K.K. Khandelwal
2. PERT & CPM - L.S.Srinath

## Slide 7
Bloom’s Category Marks (out of 120) | Tests (60) | Assignments (20) | Quizzes (20) | External Participation in Curricular/Co-Curricular Activities (20)
Remember | 10 |  | 10 | Attendance 20
Understand | 10 |  | 10 | 
Apply | 10 |  |  | 
Analyze | 10 |  |  | 
Evaluate | 10 |  |  | 
Create | 10 | 20 |  | 
Bloom’s Category | Tests
Remember | 10
Understand | 15
Apply | 15
Analyze | 15
Evaluate | 15
Create | 10
ASSESSMENT PATTERN
CIE-Continuous Internal Evaluation (120 Marks)
SEE- Semester End Examination (80 Marks)

## Slide 8
Concepts of
Project and Program
(Week 1)

## Slide 10
A project is defined as a sequence of tasks that must be completed to attain a certain outcome.
According to the Project Management Institute (PMI), the term Project refers to-
”any temporary endeavor with a definite beginning and end”.

## Slide 18
Concepts of Project Planning and Management
(Week 2-3)

## Slide 22
Real life example of
Work Breakdown Structure

## Slide 33
Project Scheduling (Bar chart)
(Week 4)

## Slide 34
Fixing False Ceiling

## Slide 37
D
D

## Slide 43
PERT and CPM
(Week 5-6)

## Slide 65
PERT: Time Estimates
(Week 7-9)

## Slide 80
Cash Flow Analysis
(Week 10-11)

## Slide 81
Internal Rate of Return (I.R.R): I.R.R of a project is the discount rate which makes its net present value equals to zero.
Payback period (PBP) is a period required for saving in cost.
PBP = (Investment cost) / (Saving or net cash flow per year).
Suitability of PBP: i. The project should be small & it is finished within a short period.
ii. When the project is profitable as soon as the investment is made.
Advantage of PBP: i. It is very simple to operate and easy to understand.
ii. Partial risk is considered.
Cash Flow Analysis

## Slide 82
Example 01: A cash-flow profile with two interest period consists of A0 = +1000, A1 = -2500, A2 = +1540. Find I.R.R per interest period.
Solution:
We know, NPV=0.
Now, 0=𝐴0𝑥 +𝐴1𝑥+𝐴2
» 1000𝑥 −2500𝑥+1540=0
» x = 1.4 or 1.1 [140% or 110%]
Now, I=x-1=1.4-1=0.4=40% or,
I=x-1=1.1-1=0.1=10% [Ans]
Cash Flow Analysis

## Slide 83
Example 02: For a project, total project cost $4.6M. Cash flows of $1M for 5 years. Find out PBP. If interest rate=0.3% / month, then what is the net present value (NPV)? Is it acceptable or not? Explain.
Solution: Part 01:
For PBP 1 year, cash-flow=-4.6+1=-3.6M $
For PBP 2 year, cash-flow =-4.6+2=-2.6M $
For PBP 3 year, cash-flow =-4.6+3=-1.6M $
For PBP 4 year, cash-flow =-4.6+4=-0.6M $
For PBP 5 year, cash-flow =-4.6+5=+0.4M $;
So, the PBP is 5 years.
Cash Flow Analysis

## Slide 84
Part 02:
= -0.097 (NPV)
The resultant NPV isn’t acceptable as this is negative. [Ans.]
Cash Flow Analysis

## Slide 85
PDCA
(Week 12)

## Slide 94
Practical Example
An example of PDCA being used in our industry:
The Architect will interpret what the customer wants with a design (Plan)
Then they will use the information to create a model (Do)
The team will run analysis and confirm design (Check) &
The model will be updated until ready for fabrication (Act)

## Slide 96
Project Monitoring and Earned Value Management
(Week 13-14)

## Slide 97
Project Monitoring refers to the process of keeping track of all project-related metrics including team performance and task duration, identifying potential problems and taking corrective actions necessary to ensure that the project is within scope, on budget and meets the specified deadlines.
It clarifies the objectives of the project, links the activities to the objectives, sets the target, reports the progress to the management and keeps the management aware of the problems which crop up during the implementation of the project.
Project Monitoring

## Slide 98: Why Project monitoring?
To assess the project results
To improve process planning
To promote learning
To understand stakeholder’s perspectives
To ensure accountability
Project Monitoring

## Slide 99: Questions have to be answered through Project Monitoring
Are tasks being carried out as planned?
Are there any unforeseen consequences that arise as a result of these tasks?
How is your team performing at a given period of time?
What are the elements of the project that needs changing?
What is the impact of these changes?
Will these actions lead you to your expected results?
Project Monitoring

## Slide 101
Earned value analysis is the project monitoring tool that is used to measure project progress which compares the actual work completed at any time with respect to the original budget and schedule.
It also compares the work achieved with the cost of achieving that work. From these three pieces of data, performance can be trended and metrics calculated to express the status of the project.
This is the practice of determining how much of the contract budget has been ‘earned’ on the basis of the actual progress which has been made to date and comparing this to the amount of cost incurred and to the planned value.
Earned Value Analysis

## Slide 103: Earned Value Calculation
Performing the earned value calculation at each predefined status points is a 5 step process.
Gather Work Performance Information
Determine Schedule Status
Determine Cost Status
Forecasting
Reporting

## Slide 104: Gathering Work Performance Information
To start, the project manager gathers four pieces of information for each task:
Budget at Completion (BAC)
Planned Value (PV)
Earned Value (EV)
Actual Cost (AC)
These are the inputs to the earned value analysis.

## Slide 105
Budget at Completion (BAC): Refers to the budget of each task. This is determined during project planning phase.
Planned Value (PV): Also called the Budgeted Cost of Work Scheduled (BCWS). It is the amount that the project is supposed to be complete up to that status point.
Earned Value (EV): Also called the Budget Cost of Work Performed (BCWP), the EV is the measure of the work performed at a specific point in time, expressed in terms of the approved budget authorized for that work. It is the amount that the project is actually complete up to that status point.

## Slide 106
Actual Cost (AC): Also called the Actual Cost of Work Performed (ACWP), the AC is the realized cost for the work performed during a specific time period. It is the actual cost of the work up to that status point. Generally, employee hours need to be converted into a cost, and all project costs need to be added up, such as the following items:
  Labor
  Materials
  Equipment
  Fixed cost items, like subcontractors

## Slide 107: Determine Schedule Status
It’s time to answer the question:
How far ahead or behind schedule is the project?
To do this, we will calculate two variables from the initial four we gathered from the project data, above:
Schedule Variance (SV)
Schedule Performance Index (SPI)

## Slide 108
Schedule Variance (SV): The schedule variance, usually abbreviated SV, tells how far ahead or behind schedule the task is in terms of the task budget. It is expressed in terms of the task budget, not the actual hours or days ahead or behind schedule.
The formula is:
SV = EV – PV
  If SV is negative, the task is behind schedule.
  If SV is zero, the task is on schedule
  If SV is positive, the task is ahead of schedule.

## Slide 109
Schedule Performance Index (SPI): The Schedule Performance Index, normally abbreviated SPI, is similar to the Schedule Variance (SV). It also tells how far ahead or behind schedule the task is in terms of the task budget, but it is a relative measure rather than an absolute one.
The formula is:
SPI = EV / PV
  If SPI is less than 1, the task is behind schedule.
  If SPI is one, the task is on schedule
  If SPI is greater than 1, the task is ahead of schedule.

## Slide 110: Determine Cost Status
In this step, we seek to answer the following question.
How far over or under budget is the project?
To do this we will calculate two more variables from the initial four we gathered from the project data.
1. Cost Variance (CV)
2. Cost Performance Index (CPI)

## Slide 111
Cost Variance (CV): The Cost Variance, usually abbreviated CV, is the amount that the task is over or under its budget. It must be calculated for each task and summed to produce the overall project’s cost variance.
The formula is:
CV = EV – AC
  If CV is negative, the task is over budget.
  If CV is zero, the task is on budget.
  If CV is positive, the task is under budget.

## Slide 112
Cost Performance Index (CPI): The Cost Performance Index, usually abbreviated CPI, like the Cost Variance, is a measure of the cost performance of the project.
The formula is:
CPI = EV / AC
If CPI is less than 1, the task is over budget.
If CPI is one, the task is on budget.
If CPI is greater than 1, the task is under budget.

## Slide 113
Project Review
(Week 15-16)

## Slide 114
Project Review
What is project review?
A Project Review is an assessment of the status of a project, at a particular point in time.
Project management review or project review is conducted to measure the deliverables produced by the project, then the results of the review are documented on the Project Review form which is presented to the sponsor for approval.

## Slide 115
Why project review is needed?
Project review helps us by stating whether the-
Project is currently delivering to schedule.
Budget allocated was sufficient at this point.
Deliverables have been produced and approved.
Risks have been controlled and mitigated.
Issues were identified and resolved.
Changes were properly managed.
Project is on track.
??
Project Review

## Slide 116
Benefits of project review
A review can-
Actually help, especially with identifying risks and issues.
Encourage good practices.
Assist in project manager and management development.
Provide early warning.
Save money in the long run.
Project Review

## Slide 117
Three tiers of players in the project review
After having some basic knowledge about project review, one question arises about who are involved in this process. The answer of this question is shown in diagram below:
Figure: Three tiers of players in the project review
Project Review

## Slide 118
Three tiers of players in the project review
The project: Includes project board members, sponsors, project manager, team leaders and project team members.
The stakeholders: Includes organizational senior management and non executives, organizational governance, and local community.
The reviewers: The project assurance team – whether internal or external to the project.
Project Review

## Slide 119
Steps to conduct a project review
Being aware of scope of the project.
Preparation of arranging schedules of interviews.
Taking sponsor, project manager and stakeholder’s interview. For all of the meetings, try to follow the same questions. This will allow any misunderstandings to be corrected before the final conclusions are reached.
Analysis of every data from the whole project.
Draft Conclusion: This will allow sponsor, project manager and stakeholder to understand the findings and importantly, the reasons for the findings.
Publish final review report.
Project Review

## Slide 120
Categories of project review
Initial review
Milestone review
Pre-implementation review
Post-implementation review
Project Review

## Slide 121
Initial review
The Initial Project Review highlights areas of risk and determines the approach to the management of project risks identified for the duration
of the project. This review supports the Project Manager through risk
assessment. The review can be carried out at any stage of the project
and can be repeated when necessary.
Project Review

## Slide 122
Milestone review
The Milestone Project Reviews are generally executed immediately after a milestone has been reached. They are meant to determine whether the phase has been completed correctly, whether the desired deliverables have been produced and whether these include a sufficient level of detail.
Depending on the nature of the project, one or more milestones may qualify for a Project Milestone Review.
Project Review

## Slide 123
Pre-implementation review
Pre-implementation Reviews highlight areas that require attention during the intensive care phase or in future projects. This type of project review helps the Project Manager by identifying ‘showstoppers’ and by focusing the effort in addressing these issues.
Such review is generally performed just before the final go-live date to determine whether progress was made on the management of the previously identified risks.
Project Review

## Slide 124
Post-implementation review
Post-implementation Project Reviews take place after the implementation date or completion of the project.
While conducting this review, following activities should be followed:
Conduct a gap analysis.
Determine whether the project goals are achieved.
Determine the satisfaction of stakeholders.
Determine the project’s cost and benefits.
Identify lessons learned and areas for further improvements.
Report findings and recommendations.
Project Review

## Slide 125
The importance of post project reviews
Post project reviews are a valuable way for teams to improve their performance and skills.
They offer a mechanism to help fuel continuous improvement as well as improve team morale.
It is important to get as many stakeholders as possible in the review since it helps to review all parts of the project.
This provides a mechanism to clear up misunderstandings and other issues.
Good planning and post meeting follow-up is crucial to make these reviews a success.
Project Review

## Slide 126
Project status report and it’s purposes
A project status report is a document that summarizes a project’s overall progress against the projected project plan.
Project status report facilitates the following:
Provide transparency into the progress toward milestones.
Help identify issues and risks, so course correction can happen quickly.
Pinpoint the progress of work done by individuals, teams, and resources.
Prevent unpleasant surprises (to team members, clients, and stakeholders).
Furnish a method for keeping project members and leaders accountable.
Present the right information to the intended audiences.
Project Review

## Slide 127
Structure of a project status report
For a status report to be comprehensive, it must include the following elements:
Summary/Overall Health of the Project.
Facts on the project progress (full information on accomplishments, timelines, and most importantly, project milestones).
Target vs. Actual Accomplishments.
Analysis.
Risks and issues (problems and challenges that the team faced).
Project Review

## Slide 128
Structure of a project status report
Action(s) taken to respond towards risks and issues.
Resources (to see how the resources are used or consumed).
Budget (to conclude if the project is under or over budget).
Schedule (to find if the project is on schedule or late).
Recommendations.
Project Review

## Slide 129
Thanks for Your Attention!